## Slide 1
UWFT Transition Planning
Sponsored Programs
(part 2 - continued from March)
April 2023 MRAM
Carol Rhodes, Vince Gonzalez, Kim Halstead
Office of Sponsored Programs | Grant & Contract Accounting | Office of Research Information Services

## Slide 2
Important Dates for Sponsored Programs
Prepping for Workday Go-live (1 of 2)
5/19: Last day to submit Change of PI Requests to OSP for PIs in “inactive” status in Workday HRP
5/31: Recommended date to submit Advance Budget Requests for awards with anticipated start dates between 6/09 and 8/01
6/07: Last day to submit Advance Extension Requests and No-Cost Extension or Temporary Budget Extension Requests for awards that end between 6/09 and 8/01
  Please submit these requests no earlier than April 15th
6/08: Final Action Date for financial reports due end of June
6/09: Last day for OSP approvals of completed Funding Actions and financial related Post Award Changes
Important dates for Sponsored Programs announcement
Notes: CAROL - Following an email we shared on xx/xx

## Slide 3
6/13: Last day to submit requests to GCA. Types of requests include:
  Transpasus
  Journal vouchers (deficit transfers, F&A cost adjustments, closeout adjustments)
  Advance Budget Requests for awards with anticipated start dates between 6/09 and 8/01
  Changes in the financial system (e.g. organization codes changes, FIN status changes)
  Cost Share additions and changes in eFECS
6/15 after 5PM: Deferred Items - Items that could not be processed will be processed after Workday Go-Live
6/22: Final Action Date for sponsor invoices due at the end of June
6/09-7/31: GCA will continue to prepare sponsor invoices and financial reports using legacy systems to ensure that sponsor deadlines are met
Important dates for Sponsored Programs announcement
Important Dates for Sponsored Programs
Prepping for Workday Go-live (2 of 2)
Notes: VINCE

## Slide 4
How will OSP & GCA Prioritize Requests after Go-Live
Notes: VINCE

## Slide 5
Prioritization of Requests after Go-Live
High Priority Items
Advance Budget Requests: New, Renewal, Extensions
Award Setup Requests: New, start date of 7/15 & earlier
Modifications:
  Supplement - awards ending between 5/1-6/30
  Renewal - start date of 7/15 & earlier
  Extension
  Temporary Budget Extension
  Restriction Release - awards ending between 5/1-6/30
  Start Date Change
  Addition of Equipment or Gov't Property
  Change in Cost Center
Other Actions: New award lines (formerly sub budgets) with start date of 7/15 & earlier
Notes: VINCE
After Go-Live, OSP and GCA will have many awards and modifications to process.
Our two offices have created this priority list to ensure the most time sensitive and impactful items receive attention they deserve:

## Slide 6
Prioritization of Requests
Medium Priority Items
Cost Share Change
Cost Share Change - requires sponsor approval
Non-competing Continuation Funding - start date of 7/16 or later
Notes: VINCE

## Slide 7
Schedule Changes:
Early Termination
Relinquishment
Funding & Budgeting Changes:
Subaward Addition
Supplement
Carry-over
Rebudgeting
De-obligation
F&A Rate Change
Programmatic Changes to:
Award Line type or other award line changes
Personnel
Key Personnel or effort
  including change in PI
Work Scope
Non-Fiscal Compliance
Other Changes to:
Location
Payment schedule
Prioritization of Requests
Low Priority Items
Notes: VINCE

## Slide 8
Business as Usual for Proposals, PANs, non-fiscal PACs, NAAs
OSP Staff training in SAGE Central
Tracking/collection of awards received from sponsor and retrieved from sponsor systems, fiscal award modifications
What if you receive an award between 6/09 -7/06?
Hang onto these and create Award Setup Requests after go-live unless the award requires acceptance during the cutover time frame
What to expect from OSP during Cutover: 6/09-7/06
Notes: CAROL

## Slide 9
What you can expect from OSP after Go-Live
All awards and modifications in SAGE Awards
You will have Award Setup Requests and Modification requests sent from OSP that need to be completed and sent back to OSP
SAGE will notify eGC1 owners when this happens
You will create Award Setup Requests and modifications and send them to OSP
Research website updates (including GIMs)
Notes: CAROL

## Slide 10
GCA - Leading up to 6/15
5/1: Communicating to departments with grants expiring in the next 60 days
5/19: Last day for GCA to initiate refunds
5/31: Soft deadline for campus to submit advance budget requests
6/8: Final Action Date for financial reports due at the end of June
6/9: Last day OSP will send final and ready to be approved Funding Actions, financial-related Post Award Changes
6/12 – 6/15: Push to process FAs, PACs, JVs, and finalize as many award closeouts as possible
Notes: VINCE

## Slide 11
GCA will be:
Running exception reports to make sure data is ready before freeze
Conducting staff training
Validating data for cutover
Updating web content
Invoicing, Reporting, Grant Tracker and GCA Help are business as usual
GCA - During Cutover 6/16-7/06
Notes: VINCE

## Slide 12
GCA - After Go-Live
GCA will be:
Entering catch-up data into Workday
Identifying and addressing any gaps in process
Developing new Key Performance Indicators
Update existing turnaround times to reflect new processes
Transitioning from GrantTracker to Award Portal
Notes: VINCE
GT/AP dates will not be confirmed until after April MRAM so we should be vague if questions come up i.e. “mid-July”

## Slide 13
ORIS: Building New Functionality in SAGE
SAGE will continue to function as usual in all areas up until the SAGE release.
SAGE Release Dates:
SAGE operational through 7/5 at 5:30 p.m. to meet the NIH deadline
7/5 starting at 5:35 p.m.: SAGE unavailable
7/6 all day: SAGE unavailable
7/7 at 6 a.m.: SAGE back online - new features available!
Key Post Go-Live Changes:
After 7/7, new awards (formerly new Funding Actions) will be entered into the SAGE Award Setup Request form
SAGE Advances will move to new SAGE Awards tab
And more! Visit UWFT for the Research Community
Notes: EMILY or KIM will present -

## Slide 14
Resources
Important Dates for Sponsored Programs: prepping for July 6th
UWFT for the Research Community
April MRAM Materials including Q&A
UWFT Change Network - Cutover Planning
Requesting:
Change of PI
Advance Budget
No-Cost Extension or Temporary Budget Extension
NEW SAGE Training Resources:
What’s Changing in SAGE? Video
SAGE Award Setup Workflow Video
SAGE Budget eLearning
Notes: EMILY or KIM will present -